## P
UniqueID | Sr. No | Product Name | Order Processing Date | Promised Delivery Date | Quantity Required | Components | Operation | Process Type | Machine Number | Run Time (min/1000) | Cycle Time (seconds) | Setup time (seconds) | Start Time | End Time | status
7 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C1 | Op1 | In House | M1 | 30 | 3 | 0 |  |  | InProgress
8 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C2 | Op2 | In House | M2 | 30 | 7.2 | 10000 |  |  | InProgress
9 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C3 | Op3 | Outsource | OutSrc | 75 |  | 0 |  |  | InProgress
1 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C1 | Op1 | In House | M1 | 10 | 1.08 | 10000 |  |  | InProgress
2 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C2 | Op2 | Outsource | OutSrc | 200 |  | 10000 |  |  | InProgress
3 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C3 | Op3 | In House | M2 | 20 | 7.2 | 10000 |  |  | InProgress
4 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C4 | Op4 | In House | M1 | 30 | 1.08 | 10000 |  |  | InProgress
5 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C5 | Op5 | In House | M3 | 15 | 7.2 | 10000 |  |  | InProgress
6 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C6 | Op5 | In House | M3 | 14 | 7.2 | 10000 |  |  | InProgress
16 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C1 | Op1 | In House | M1 | 40 | 1.08 | 10000 |  |  | InProgress
17 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C2 | Op2 | In House | M2 | 40 | 7.2 | 10000 |  |  | InProgress
18 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C3 | Op3 | In House | M2 | 35 | 7.2 | 10000 |  |  | InProgress
10 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C1 | Op1 | Outsource | OutSrc | 185 |  | 10000 |  |  | InProgress
11 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C2 | Op2 | In House | M1 | 30 | 1.08 | 10000 |  |  | InProgress
12 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C3 | Op3 | In House | M2 | 40 | 7.2 | 10000 |  |  | InProgress
13 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C1 | Op1 | Outsource | OutSrc | 65 | 1.08 | 10000 |  |  | InProgress
14 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C2 | Op2 | In House | M1 | 35 |  | 10000 |  |  | InProgress
15 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C3 | Op3 | In House | M2 | 30 | 7.2 | 10000 |  |  | InProgress
20 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C1 | Op1 | In House | M1 | 30 | 7.2 | 10000 |  |  | InProgress
21 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C2 | Op2 | In House | M2 | 30 |  | 10000 |  |  | InProgress
22 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C3 | Op3 | In House | M3 | 30 | 1.08 | 10000 |  |  | InProgress
24 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 8000 | C1 | Op4 | In House | M2 | 90 | 2.9 | 10000 |  |  | InProgress
23 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 8000 | C2 | Op4 | In House | M3 | 90 | 2 | 10000 |  |  | InProgress

## prodet
UniqueID | Sr. No | Product Name | Order Processing Date | Promised Delivery Date | Quantity Required | Components | Operation | Process Type | Machine Number | Run Time (min/1000) | Cycle Time (seconds) | Setup time (seconds) | Start Time | End Time | status | legend | wait_time
7 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C1 | Op1 | In House | M1 | 30 | 3 | 0 | 2024-08-21 09:00 | 2024-08-21 11:00 | InProgress | C1 | 0
24 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 1333 | C1 | Op4 | In House | M2 | 90 | 2.9 | 10000 | 2024-08-21 09:00 | 2024-08-21 11:00 | InProgress | C1 | 0
13 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C1 | Op1 | Outsource | OutSrc | 65 | 1.08 | 10000 | 2024-08-21 09:00 | 2024-08-21 14:25 | InProgress | OutSrc | 0
10 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C1 | Op1 | Outsource | OutSrc | 185 |  | 10000 | 2024-08-21 09:00 | 2024-08-28 15:15 | InProgress | OutSrc | 0
1 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C1 | Op1 | In House | M1 | 10 | 1.08 | 10000 | 2024-08-21 11:00 | 2024-08-21 12:30 | InProgress | C1 | 0.083333
8 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C2 | Op2 | In House | M2 | 30 | 7.2 | 10000 | 2024-08-21 11:00 | 2024-08-21 13:00 | InProgress | C2 | 0.083333
16 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C1 | Op1 | In House | M1 | 40 | 1.08 | 10000 | 2024-08-21 12:30 | 2024-08-21 14:30 | InProgress | C1 | 0.14583
2 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C2 | Op2 | Outsource | OutSrc | 200 |  | 10000 | 2024-08-21 12:30 | 2024-08-27 10:30 | InProgress | OutSrc | 0.14583
24 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 1000 | C1 | Op4 | In House | M2 | 90 | 2.9 | 10000 | 2024-08-21 13:00 | 2024-08-21 14:30 | InProgress | C1 | 0.16667
9 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C3 | Op3 | Outsource | OutSrc | 75 |  | 0 | 2024-08-21 13:00 | 2024-08-22 10:00 | InProgress | OutSrc | 0.16667
17 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C2 | Op2 | In House | M2 | 40 | 7.2 | 10000 | 2024-08-21 14:30 | 2024-08-21 16:30 | InProgress | C2 | 0.22917
14 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C2 | Op2 | In House | M1 | 35 |  | 10000 | 2024-08-21 14:30 | 2024-08-22 09:25 | InProgress | C2 | 0.22917
18 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C3 | Op3 | In House | M2 | 35 | 7.2 | 10000 | 2024-08-21 16:30 | 2024-08-22 10:15 | InProgress | C3 | 0.3125
20 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C1 | Op1 | In House | M1 | 30 | 7.2 | 10000 | 2024-08-22 09:25 | 2024-08-22 11:25 | InProgress | C1 | 0.35069
15 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C3 | Op3 | In House | M2 | 30 | 7.2 | 10000 | 2024-08-22 10:15 | 2024-08-22 12:45 | InProgress | C3 | 0.38542
21 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C2 | Op2 | In House | M2 | 30 |  | 10000 | 2024-08-22 12:45 | 2024-08-22 14:45 | InProgress | C2 | 0.48958
22 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C3 | Op3 | In House | M3 | 30 | 1.08 | 10000 | 2024-08-22 14:45 | 2024-08-22 16:45 | InProgress | C3 | 0.57292
24 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 5667 | C1 | Op4 | In House | M2 | 90 | 2.9 | 10000 | 2024-08-22 14:45 | 2024-08-23 15:15 | InProgress | C1 | 0.57292
23 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 8000 | C2 | Op4 | In House | M3 | 90 | 2 | 10000 | 2024-08-23 15:15 | 2024-08-27 11:15 | InProgress | C2 | 0.92708
3 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C3 | Op3 | In House | M2 | 20 | 7.2 | 10000 | 2024-08-27 10:30 | 2024-08-27 13:30 | InProgress | C3 | 1.3958
4 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C4 | Op4 | In House | M1 | 30 | 1.08 | 10000 | 2024-08-27 13:30 | 2024-08-28 10:00 | InProgress | C4 | 1.5208
5 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C5 | Op5 | In House | M3 | 15 | 7.2 | 10000 | 2024-08-28 10:00 | 2024-08-28 12:15 | InProgress | C5 | 1.7083
6 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C6 | Op5 | In House | M3 | 14 | 7.2 | 10000 | 2024-08-28 12:15 | 2024-08-28 14:21 | InProgress | C6 | 1.8021
11 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C2 | Op2 | In House | M1 | 30 | 1.08 | 10000 | 2024-08-28 15:15 | 2024-08-29 14:45 | InProgress | C2 | 1.9271
12 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C3 | Op3 | In House | M2 | 40 | 7.2 | 10000 | 2024-08-29 14:45 | 2024-08-30 16:45 | InProgress | C3 | 2.2396

## Machine Utilisation
Machine Number | Daily Utilization
M1 | 0.47656
M2 | 0.46875
M3 | 0.30781

## Product Waiting Time
| Product Name | Average Days | Formatted Time
0 | Product 1 | 1.11 | 1 days 2 hours
1 | Product 2 | 0.08 | 0 days 2 hours
2 | Product 3 | 1.39 | 1 days 9 hours
3 | Product 4 | 0.2 | 0 days 4 hours
4 | Product 5 | 0.23 | 0 days 5 hours
5 | Product 6 | 0.47 | 0 days 11 hours
6 | Product 7 | 0.42 | 0 days 10 hours

## Component Waiting Time
| Components | Average Days | Formatted Time
0 | C1 | 0.15 | 0 days 3 hours
1 | C2 | 0.58 | 0 days 13 hours
2 | C3 | 0.85 | 0 days 20 hours
3 | C4 | 1.52 | 1 days 12 hours
4 | C5 | 1.71 | 1 days 17 hours
5 | C6 | 1.8 | 1 days 19 hours

## Late Products
| late | count
0 | late | 1
1 | on time | 6